## Resumen
Asignación de tareas — Regla de oro: 1 feature = 1 responsable
Cada feature completa (backend + frontend + tests) tiene UN solo desarrollador responsable.
Si un desarrollador tiene pocas tareas, se le asignan features adicionales aunque no sean de su especialidad.
Usa al agent para lo que no domines. Siempre sincronizá contra upstream/main antes de empezar.
════════════════════════════════════════════════════════════
Nest/Owner — 3 features (52 tareas)
Dueño de: admin-auth-core, direct-purchase, custom-quote.
Backend NestJS en services/api-core/src/modules/*.
Frontend en apps/landing y apps/admin-dashboard.
Único que mergea y revisa PRs financieros como segundo reviewer humano.
DB — 3 features (35 tareas)
Dueño de: catalog-landing, supply-stock-management, order-delivery-schedule.
Migraciones/schema (Prisma) de TODAS las features.
Backend de features orientadas a datos. También: .env.example, seed-db.sh.
Java — 2 features (31 tareas)
Dueño de: payment-billing-java, infra-deploy.
Microservicio aislado payment-service (DB propia, solo HTTP).
Infraestructura: Docker, CI/CD, Nginx, Turborepo.
Design — 4 features (42 tareas)
Dueño de: realtime-notifications, quote-management-admin, complaints-refunds, i18n-localization.
Frontend de TODAS las features (apps/landing, apps/admin-dashboard).
Backend NestJS de features asignadas (usa al agent para migraciones/endpoints).
════════════════════════════════════════════════════════════
Reglas para dependencias entre personas
• Si tu tarea depende de otra de OTRA persona: no empieces hasta que esa tarea tenga PR mergeado.
• Si tu tarea depende de otra TUYA: seguí el orden de la columna 'Depende de' en la hoja Tareas.
• Las migraciones (DB) siempre van primero en cada feature.
• Coordinación obligatoria antes de tocar módulos de otros (ver columna Notas).
• Nunca commitees a main sin aprobación del owner.
• Siempre sincronizá contra upstream/main antes de empezar.

## Features
Feature | Responsable | Descripción | Tareas | Dependencias de feature | Estado
feature-admin-auth-core | Nest/Owner | Autenticación y control de acceso admin | 15 | Ninguna (feature base) | Pendiente
feature-direct-purchase | Nest/Owner | Flujo A: compra directa del catálogo público | 15 | catalog-landing | Pendiente
feature-custom-quote | Nest/Owner | Flujo B: cotización personalizada completa | 23 | Ninguna (feature base) | Pendiente
feature-catalog-landing | DB | Catálogo público en landing con SSE | 14 | Ninguna (feature base) | Pendiente
feature-supply-stock-management | DB | Gestión de insumos y stock con importación Excel | 13 | Ninguna (feature base) | Pendiente
feature-order-delivery-schedule | DB | Vista unificada de entregas con calendario | 8 | direct-purchase, custom-quote | Pendiente
feature-payment-billing-java | Java | Microservicio de pagos y facturación (Spring Boot) | 17 | Ninguna (feature aislada) | Pendiente
feature-infra-deploy | Java | Docker, CI/CD, Nginx, despliegue | 14 | Ninguna (feature base) | Pendiente
feature-realtime-notifications | Design | Notificaciones WebSocket en tiempo real para admin | 12 | admin-auth-core | Pendiente
feature-quote-management-admin | Design | Vista admin de gestión de cotizaciones | 8 | custom-quote | Pendiente
feature-complaints-refunds | Design | Reclamos, aprobación de reembolsos | 12 | Ninguna (feature base) | Pendiente
feature-i18n-localization | Design | Internacionalización es/en de la aplicación | 10 | direct-purchase, custom-quote, complaints-refunds | Pendiente
TOTAL

## Tareas
Feature/Flujo | Task ID | Descripción | Carpeta / Módulo | Asignado a | Depende de | Notas
feature-admin-auth-core | TASK-auth-1 | Migración tablas admin_users, refresh_tokens | services/api-core/prisma/migrations | DB | none
feature-admin-auth-core | TASK-auth-2 | Hash de password (argon2) + entidad AdminUser | services/api-core/src/modules/auth | Nest/Owner | TASK-auth-1
feature-admin-auth-core | TASK-auth-3 | POST /admin/auth/login (JWT + refresh cookie) | services/api-core/src/modules/auth | Nest/Owner | TASK-auth-2
feature-admin-auth-core | TASK-auth-4 | POST /admin/auth/refresh | services/api-core/src/modules/auth | Nest/Owner | TASK-auth-3
feature-admin-auth-core | TASK-auth-5 | POST /admin/auth/logout (revoca refresh) | services/api-core/src/modules/auth | Nest/Owner | TASK-auth-3
feature-admin-auth-core | TASK-auth-6 | Rate limiting en login (Redis) | services/api-core/src/modules/auth | Nest/Owner | TASK-auth-3
feature-admin-auth-core | TASK-auth-7 | Guard JWT global para /admin/** | services/api-core/src/modules/auth | Nest/Owner | TASK-auth-3 | Bloquea endpoints admin de otras features
feature-admin-auth-core | TASK-auth-8 | Endpoints crear/desactivar admin | services/api-core/src/modules/auth | Nest/Owner | TASK-auth-2
feature-admin-auth-core | TASK-auth-9 | views/LoginPage + controllers/useAuth.ts | apps/admin-dashboard | Nest/Owner | TASK-auth-3
feature-admin-auth-core | TASK-auth-10 | views/DashboardLayout con nav lateral | apps/admin-dashboard | Nest/Owner | TASK-auth-9
feature-admin-auth-core | TASK-auth-11 | Interceptor HTTP de refresh automático | apps/admin-dashboard | Nest/Owner | TASK-auth-9, TASK-auth-4
feature-admin-auth-core | TASK-auth-12 | CI workflow (lint/test/build) monorepo | raiz repo / .github | Nest/Owner | none | Puede arrancar en paralelo desde el día 1
feature-admin-auth-core | TASK-auth-13 | Notificación admin en lockout por rate-limit | services/api-core/src/modules/auth | Nest/Owner | TASK-auth-6, TASK-notif-3
feature-admin-auth-core | TASK-auth-test1 | Unit tests: password hashing, JWT, rate limit | services/api-core/src/modules/auth/__tests__ | Nest/Owner | TASK-auth-8
feature-admin-auth-core | TASK-auth-test2 | Integration tests: endpoints + guard | services/api-core/src/modules/auth/__tests__ | Nest/Owner | TASK-auth-11
feature-direct-purchase | TASK-directpurchase-1 | Migración tabla orders | services/api-core/prisma/migrations | DB | none
feature-direct-purchase | TASK-directpurchase-2 | Entidad Order + máquina de estados (guards) | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-1
feature-direct-purchase | TASK-directpurchase-3 | POST /orders (re-lee precio/stock server-side) | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-2, TASK-catalog-2
feature-direct-purchase | TASK-directpurchase-4 | Cliente HTTP a payment-service para iniciar pago | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-3 | Contra contrato mockeado si payment-service no está mergeado
feature-direct-purchase | TASK-directpurchase-5 | Webhook POST /orders/webhooks/payment-result | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-4
feature-direct-purchase | TASK-directpurchase-6 | Email de confirmación de pago al cliente | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-5
feature-direct-purchase | TASK-directpurchase-7 | Notificación WebSocket a admin (nueva compra) | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-5, TASK-notif-3
feature-direct-purchase | TASK-directpurchase-8 | PATCH /orders/:id/accept (descuenta stock, ETA) | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-5
feature-direct-purchase | TASK-directpurchase-9 | PATCH /orders/:id/reject (motivo + reembolso auto) | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-5 | Financiero: segundo reviewer humano obligatorio
feature-direct-purchase | TASK-directpurchase-10 | BullMQ reconciliation job para pagos colgados | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-4
feature-direct-purchase | TASK-directpurchase-11 | Admin listing GET /orders con filtros/búsqueda/paginación | services/api-core/src/modules/orders | Nest/Owner | TASK-directpurchase-2
feature-direct-purchase | TASK-directpurchase-12 | Landing UI — botón 'Comprar' y pantalla de resultado de pago | apps/landing | Nest/Owner | TASK-directpurchase-3
feature-direct-purchase | TASK-directpurchase-13 | Admin UI — tabla de órdenes pendientes con aceptar/rechazar | apps/admin-dashboard | Nest/Owner | TASK-directpurchase-11
feature-direct-purchase | TASK-directpurchase-test1 | Unit tests: order state machine guards | services/api-core/src/modules/orders/__tests__ | Nest/Owner | TASK-directpurchase-9
feature-direct-purchase | TASK-directpurchase-test2 | Integration tests: flujo completo de compra (mock payment-service) | services/api-core/src/modules/orders/__tests__ | Nest/Owner | TASK-directpurchase-13
feature-custom-quote | TASK-quoteB-1 | Migración tabla quotes | services/api-core/prisma/migrations | DB | none
feature-custom-quote | TASK-quoteB-2 | Entidad Quote + máquina de estados con guards | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-1
feature-custom-quote | TASK-quoteB-3 | POST /quotes con validación estricta name/email/phone | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-2
feature-custom-quote | TASK-quoteB-4 | Descarte por datos incompletos + notificación admin | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-3
feature-custom-quote | TASK-quoteB-5 | Email de confirmación 'recibido, pendiente' | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-3
feature-custom-quote | TASK-quoteB-6 | PATCH /quotes/:id/present (admin cotiza) | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-2
feature-custom-quote | TASK-quoteB-7 | Token firmado (JWT) de un solo uso accept/reject | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-6
feature-custom-quote | TASK-quoteB-8 | Email con botones accept/reject (deep link) | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-7
feature-custom-quote | TASK-quoteB-9 | GET /quotes/:id/accept (verificación + transacción) | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-7
feature-custom-quote | TASK-quoteB-10 | GET /quotes/:id/reject (mismos criterios de seguridad) | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-7
feature-custom-quote | TASK-quoteB-11 | Notificación admin en rechazo (para archivado) | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-10
feature-custom-quote | TASK-quoteB-12 | Integración payment-service (link de pago, deadline 24h) | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-9 | Contrato mockeado si payment-service no está listo
feature-custom-quote | TASK-quoteB-webhook | Webhook POST /api/quotes/webhooks/payment-result | services/api-core/src/modules/quotes/interface/http | Nest/Owner | TASK-quoteB-12
feature-custom-quote | TASK-quoteB-13 | Job BullMQ quote-expiration-check (48h sin respuesta) | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-6
feature-custom-quote | TASK-quoteB-14 | Job BullMQ quote-payment-expiration-check (24h sin pago) | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-webhook
feature-custom-quote | TASK-quoteB-15 | PATCH /quotes/:id/archive | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-13, TASK-quoteB-14
feature-custom-quote | TASK-quoteB-16 | Listado admin GET /quotes con filtros | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-2
feature-custom-quote | TASK-quoteB-17 | UI landing — formulario de solicitud de cotización | apps/landing | Nest/Owner | TASK-quoteB-3
feature-custom-quote | TASK-quoteB-18 | Páginas públicas resultado accept/reject | apps/landing | Nest/Owner | TASK-quoteB-9, TASK-quoteB-10
feature-custom-quote | TASK-quoteB-19 | UI admin — pantalla de cotizar (precio + plazo) | apps/admin-dashboard | Nest/Owner | TASK-quoteB-6
feature-custom-quote | TASK-quoteB-20 | Notificación admin al completar pago + timer entrega | services/api-core/src/modules/quotes | Nest/Owner | TASK-quoteB-webhook
feature-custom-quote | TASK-quoteB-test1 | Unit tests: quote state machine + lógica de tokens | services/api-core/src/modules/quotes/__tests__ | Nest/Owner | TASK-quoteB-15
feature-custom-quote | TASK-quoteB-test2 | Integration tests: ciclo completo de cotización | services/api-core/src/modules/quotes/__tests__ | Nest/Owner | TASK-quoteB-20
feature-catalog-landing | TASK-catalog-1 | Migración prototypes + proto_images | services/api-core/prisma/migrations | DB | none
feature-catalog-landing | TASK-catalog-2 | Entidad Prototype + reglas (active implica visible, stock_qty >= 0) | services/api-core/src/modules/catalog | DB | TASK-catalog-1
feature-catalog-landing | TASK-catalog-3 | GET /catalog/prototypes con filtros + paginación | services/api-core/src/modules/catalog | DB | TASK-catalog-2
feature-catalog-landing | TASK-catalog-4 | GET /catalog/prototypes/:id | services/api-core/src/modules/catalog | DB | TASK-catalog-2
feature-catalog-landing | TASK-catalog-5 | Cache Redis con invalidación en update | services/api-core/src/modules/catalog | DB | TASK-catalog-3
feature-catalog-landing | TASK-catalog-6 | SSE /catalog/stream + event publisher | services/api-core/src/modules/catalog | DB | TASK-catalog-2
feature-catalog-landing | TASK-catalog-7 | models/catalogApi.ts (fetch + EventSource) | apps/landing | DB | TASK-catalog-3, TASK-catalog-6
feature-catalog-landing | TASK-catalog-8 | controllers/useCatalog.ts (merge SSE + backoff reconexión) | apps/landing | DB | TASK-catalog-7
feature-catalog-landing | TASK-catalog-9 | views/CatalogGrid + PrototypeCard (mobile-first) | apps/landing | DB | TASK-catalog-8
feature-catalog-landing | TASK-catalog-10 | views/PrototypeDetail + galería de imágenes | apps/landing | DB | TASK-catalog-8
feature-catalog-landing | TASK-catalog-11 | views/CatalogFilters (categoría, precio, búsqueda) | apps/landing | DB | TASK-catalog-8
feature-catalog-landing | TASK-catalog-12 | Aviso 'ya no disponible' vía evento SSE prototype.deactivated | apps/landing | DB | TASK-catalog-9, TASK-catalog-6
feature-catalog-landing | TASK-catalog-test1 | Unit tests: reglas de dominio del catálogo | services/api-core/src/modules/catalog/__tests__ | DB | TASK-catalog-6
feature-catalog-landing | TASK-catalog-test2 | Integration tests: endpoints catálogo + SSE | services/api-core/src/modules/catalog/__tests__ | DB | TASK-catalog-12
feature-supply-stock-management | TASK-stock-1 | Migración supplies, supply_stock_change_log, low_stock_alert_state | services/api-core/prisma/migrations | DB | none
feature-supply-stock-management | TASK-stock-2 | Entidad Supply + reglas (cantidad no negativa) | services/api-core/src/modules/supplies | DB | TASK-stock-1
feature-supply-stock-management | TASK-stock-3 | CRUD /admin/supplies + filtros/búsqueda/paginación | services/api-core/src/modules/supplies | DB | TASK-stock-2
feature-supply-stock-management | TASK-stock-4 | Parser Excel (lectura) + validación fila por fila | services/api-core/src/modules/supplies | DB | TASK-stock-2
feature-supply-stock-management | TASK-stock-5 | Endpoint import-excel (preview sin aplicar) | services/api-core/src/modules/supplies | DB | TASK-stock-4
feature-supply-stock-management | TASK-stock-6 | Endpoint import-excel/confirm (aplica + log de cambios) | services/api-core/src/modules/supplies | DB | TASK-stock-5
feature-supply-stock-management | TASK-stock-7 | Endpoint export-excel | services/api-core/src/modules/supplies | DB | TASK-stock-3
feature-supply-stock-management | TASK-stock-8 | Job BullMQ hourly-low-stock-check (anti-fatiga alertas) | services/api-core/src/modules/supplies | DB | TASK-stock-3, feature-realtime-notifications | Llama a notifyAdmins() — solo consume la función
feature-supply-stock-management | TASK-stock-9 | views/SuppliesTable + SupplyForm | apps/admin-dashboard | DB | TASK-stock-3
feature-supply-stock-management | TASK-stock-10 | views/ExcelImportWizard (preview con diffs) | apps/admin-dashboard | DB | TASK-stock-5, TASK-stock-6
feature-supply-stock-management | TASK-stock-11 | Plantilla .xlsx descargable + docs/supply-template.md | docs/ + apps/admin-dashboard | DB | TASK-stock-4
feature-supply-stock-management | TASK-stock-test1 | Unit tests: reglas de dominio supply + lógica alertas | services/api-core/src/modules/supplies/__tests__ | DB | TASK-stock-8
feature-supply-stock-management | TASK-stock-test2 | Integration tests: CRUD supplies + import/export Excel | services/api-core/src/modules/supplies/__tests__ | DB | TASK-stock-11
feature-order-delivery-schedule | TASK-delivery-1 | Vista SQL/proyección DeliveryItem (UNION orders+quotes) | services/api-core/prisma + src/modules/deliveries | DB | TASK-directpurchase-2, TASK-quoteB-2
feature-order-delivery-schedule | TASK-delivery-2 | GET /admin/deliveries con filtros/búsqueda/paginación | services/api-core/src/modules/deliveries | DB | TASK-delivery-1
feature-order-delivery-schedule | TASK-delivery-3 | PATCH /admin/deliveries/:origin/:id/deliver | services/api-core/src/modules/deliveries | DB | TASK-delivery-1
feature-order-delivery-schedule | TASK-delivery-4 | PATCH /admin/deliveries/:origin/:id/postpone | services/api-core/src/modules/deliveries | DB | TASK-delivery-1
feature-order-delivery-schedule | TASK-delivery-5 | views/DeliveriesBoard (calendario/lista, indicador overdue) | apps/admin-dashboard | DB | TASK-delivery-2
feature-order-delivery-schedule | TASK-delivery-6 | views/DeliveriesTable | apps/admin-dashboard | DB | TASK-delivery-2
feature-order-delivery-schedule | TASK-delivery-test1 | Unit tests: proyección delivery + lógica overdue | services/api-core/src/modules/deliveries/__tests__ | DB | TASK-delivery-4
feature-order-delivery-schedule | TASK-delivery-test2 | Integration tests: DeliveryItem projection + acciones | services/api-core/src/modules/deliveries/__tests__ | DB | TASK-delivery-6
feature-payment-billing-java | TASK-pay-1 | Scaffold proyecto Spring Boot (Maven), estructura de paquetes | services/payment-service | Java | none | Feature aislada: DB propia, solo habla HTTP
feature-payment-billing-java | TASK-pay-2 | Configurar conexión DB propia (Postgres/Supabase) + Flyway | services/payment-service | Java | TASK-pay-1
feature-payment-billing-java | TASK-pay-3 | Entidades JPA: Payment, Refund, Receipt, AuditLog | services/payment-service | Java | TASK-pay-2
feature-payment-billing-java | TASK-pay-4 | Integración PayPal Orders API SDK/REST (sandbox) | services/payment-service | Java | TASK-pay-1
feature-payment-billing-java | TASK-pay-5 | POST /payments/orders con idempotency_key | services/payment-service | Java | TASK-pay-3, TASK-pay-4
feature-payment-billing-java | TASK-pay-6 | Webhook POST /payments/webhooks/paypal (firma + dedup) | services/payment-service | Java | TASK-pay-4
feature-payment-billing-java | TASK-pay-7 | Generación de recibo PDF (cliente + admin) | services/payment-service | Java | TASK-pay-6
feature-payment-billing-java | TASK-pay-8 | Envío de recibo por email con retry | services/payment-service | Java | TASK-pay-7
feature-payment-billing-java | TASK-pay-9 | Webhook saliente a api-core notificando resultado de pago | services/payment-service | Java | TASK-pay-6 | Contrato definido en design.md de direct-purchase
feature-payment-billing-java | TASK-pay-10 | Integración PayPal Refunds API | services/payment-service | Java | TASK-pay-4
feature-payment-billing-java | TASK-pay-11 | POST /payments/orders/:ref/refund con idempotencia | services/payment-service | Java | TASK-pay-10, TASK-pay-3
feature-payment-billing-java | TASK-pay-12 | Generación y envío de recibo de reembolso | services/payment-service | Java | TASK-pay-11
feature-payment-billing-java | TASK-pay-13 | Audit log inmutable de toda operación financiera | services/payment-service | Java | TASK-pay-3
feature-payment-billing-java | TASK-pay-14 | GET /payments/:ref/receipt | services/payment-service | Java | TASK-pay-7
feature-payment-billing-java | TASK-pay-15 | Tests de idempotencia (obligatorio antes de mergear) | services/payment-service | Java | TASK-pay-5, TASK-pay-11 | Doble reviewer humano obligatorio (steering 03)
feature-payment-billing-java | TASK-pay-test1 | Unit tests: lógica de dominio de pagos (JUnit) | services/payment-service/src/test/java | Java | TASK-pay-13
feature-payment-billing-java | TASK-pay-test2 | Integration tests: flujo completo PayPal sandbox | services/payment-service/src/test/java | Java | TASK-pay-15
feature-infra-deploy | TASK-infra-1 | Setup Turborepo raíz (turbo.json, workspaces) | raiz repo | Java | none | Puede arrancar en paralelo desde el día 1
feature-infra-deploy | TASK-infra-2 | Dockerfile multi-stage para api-core | services/api-core | Java | TASK-infra-1
feature-infra-deploy | TASK-infra-3 | Dockerfile multi-stage para payment-service (Maven + JRE) | services/payment-service | Java | none
feature-infra-deploy | TASK-infra-4 | Dockerfile build para landing + admin-dashboard (Nginx) | apps/landing, apps/admin-dashboard | Java | TASK-infra-1
feature-infra-deploy | TASK-infra-5 | Configuración Nginx (reverse proxy + estáticos) | infra/ | Java | TASK-infra-2, TASK-infra-3, TASK-infra-4
feature-infra-deploy | TASK-infra-6 | docker-compose.yml (dev) integrando todo + Redis local | infra/ | Java | TASK-infra-5 | Momento de verdad: integración real
feature-infra-deploy | TASK-infra-7 | .env.example con todas las variables documentadas | raiz repo | Java | none
feature-infra-deploy | TASK-infra-8 | scripts/seed-db.sh + seeder TS con faker | scripts/ | Java | TASK-infra-6
feature-infra-deploy | TASK-infra-9 | Extender pipeline CI (Docker build, job Maven paralelo) | .github/workflows | Java | TASK-infra-1, TASK-auth-12
feature-infra-deploy | TASK-infra-10 | Job build/push de imagen payment-service en paralelo | .github/workflows | Java | TASK-infra-3, TASK-infra-9
feature-infra-deploy | TASK-infra-11 | Documentar despliegue por ambiente (docs/deployment.md) | docs/ | Java | TASK-infra-6
feature-infra-deploy | TASK-infra-12 | scripts/prod-up.sh para despliegue en producción | scripts/ | Java | TASK-infra-6
feature-infra-deploy | TASK-infra-test1 | Integration test: docker-compose dev environment | infra/__tests__ | Java | TASK-infra-6
feature-infra-deploy | TASK-infra-test2 | Validación CI pipeline (en PR real) | .github/workflows | Java | TASK-infra-9
feature-realtime-notifications | TASK-notif-1 | Migración tabla admin_notifications | services/api-core/prisma/migrations | DB | none
feature-realtime-notifications | TASK-notif-2 | Módulo notifications + función central notifyAdmins() | services/api-core/src/modules/notifications | Design | TASK-notif-1 | Punto de entrada único, lo usan otras features
feature-realtime-notifications | TASK-notif-3 | WebSocket Gateway (@nestjs/websockets) con auth JWT en handshake | services/api-core/src/modules/notifications | Design | TASK-notif-2, feature-admin-auth-core
feature-realtime-notifications | TASK-notif-4 | GET /admin/notifications?read=&page= | services/api-core/src/modules/notifications | Design | TASK-notif-2
feature-realtime-notifications | TASK-notif-5 | Evento notification.mark_read (propagado a multi-tab) | services/api-core/src/modules/notifications | Design | TASK-notif-3
feature-realtime-notifications | TASK-notif-6 | Integrar notifyAdmins() en: purchase, quotes, complaints, low-stock | services/api-core/src/modules/* (varios) | Design | TASK-notif-2, TASK-directpurchase-7, TASK-quoteB-11, TASK-complaint-4, TASK-stock-8 | Toca módulos de otras features: coordinar antes de tocar
feature-realtime-notifications | TASK-notif-7 | controllers/useNotifications.ts (socket + cola sonido con debounce) | apps/admin-dashboard | Design | TASK-notif-3
feature-realtime-notifications | TASK-notif-8 | views/NotificationBell + views/NotificationPanel | apps/admin-dashboard | Design | TASK-notif-7
feature-realtime-notifications | TASK-notif-9 | Asset de sonido + preferencia on/off persistida | apps/admin-dashboard | Design | TASK-notif-8
feature-realtime-notifications | TASK-notif-10 | Reconexión con backoff en cliente WebSocket | apps/admin-dashboard | Design | TASK-notif-7
feature-realtime-notifications | TASK-notif-test1 | Unit tests: lógica del módulo notifications | services/api-core/src/modules/notifications/__tests__ | Design | TASK-notif-5
feature-realtime-notifications | TASK-notif-test2 | Integration tests: WebSocket + entrega de eventos SSE | services/api-core/src/modules/notifications/__tests__ | Design | TASK-notif-10
feature-quote-management-admin | TASK-quoteadmin-1 | GET /admin/quotes con filtros combinados | services/api-core/src/modules/quotes | Design | TASK-quoteB-16
feature-quote-management-admin | TASK-quoteadmin-2 | GET /admin/quotes/:id con timeline calculada | services/api-core/src/modules/quotes | Design | TASK-quoteadmin-1
feature-quote-management-admin | TASK-quoteadmin-3 | PATCH /admin/quotes/:id/postpone + email a cliente | services/api-core/src/modules/quotes | Design | TASK-quoteadmin-1
feature-quote-management-admin | TASK-quoteadmin-4 | views/QuotesTable (tabs/filtros/paginación) | apps/admin-dashboard | Design | TASK-quoteadmin-1
feature-quote-management-admin | TASK-quoteadmin-5 | views/QuoteDetail + componente TimelineStatus | apps/admin-dashboard | Design | TASK-quoteadmin-2 | TimelineStatus candidato a packages/ compartido
feature-quote-management-admin | TASK-quoteadmin-6 | views/PostponeQuoteModal | apps/admin-dashboard | Design | TASK-quoteadmin-3
feature-quote-management-admin | TASK-quoteadmin-test1 | Unit tests: lógica de admin quote management | services/api-core/src/modules/quotes/__tests__ | Design | TASK-quoteadmin-3
feature-quote-management-admin | TASK-quoteadmin-test2 | Integration tests: admin quote management | services/api-core/src/modules/quotes/__tests__ | Design | TASK-quoteadmin-6
feature-complaints-refunds | TASK-complaint-1 | Migración tabla complaints | services/api-core/prisma/migrations | DB | none
feature-complaints-refunds | TASK-complaint-2 | Entidad Complaint + POST /complaints | services/api-core/src/modules/complaints | Design | TASK-complaint-1
feature-complaints-refunds | TASK-complaint-3 | Email recibo de reclamo (con número de referencia) | services/api-core/src/modules/complaints | Design | TASK-complaint-2
feature-complaints-refunds | TASK-complaint-4 | Notificación admin de nuevo reclamo | services/api-core/src/modules/complaints | Design | TASK-complaint-2
feature-complaints-refunds | TASK-complaint-5 | GET /admin/complaints con filtros/búsqueda/paginación | services/api-core/src/modules/complaints | Design | TASK-complaint-2
feature-complaints-refunds | TASK-complaint-review | PATCH /admin/complaints/:id/review (received → under_review) | services/api-core/src/modules/complaints | Design | TASK-complaint-2
feature-complaints-refunds | TASK-complaint-6 | PATCH /admin/complaints/:id/approve-refund (integración payment-service) | services/api-core/src/modules/complaints | Design | TASK-complaint-2, TASK-pay-11 | Financiero: segundo reviewer humano obligatorio
feature-complaints-refunds | TASK-complaint-7 | PATCH /admin/complaints/:id/resolve | services/api-core/src/modules/complaints | Design | TASK-complaint-2
feature-complaints-refunds | TASK-complaint-8 | views/ComplaintForm en landing | apps/landing | Design | TASK-complaint-2
feature-complaints-refunds | TASK-complaint-9 | views/ComplaintsTable + ComplaintDetail en admin | apps/admin-dashboard | Design | TASK-complaint-5
feature-complaints-refunds | TASK-complaint-test1 | Unit tests: transiciones de estado de complaint | services/api-core/src/modules/complaints/__tests__ | Design | TASK-complaint-7
feature-complaints-refunds | TASK-complaint-test2 | Integration tests: flujo completo de reclamo | services/api-core/src/modules/complaints/__tests__ | Design | TASK-complaint-9
feature-i18n-localization | TASK-i18n-1 | Setup react-i18next en apps/landing + estructura de archivos de traducción | apps/landing | Design | none
feature-i18n-localization | TASK-i18n-2 | controllers/useLocale.ts (detección + persistencia) | apps/landing | Design | TASK-i18n-1
feature-i18n-localization | TASK-i18n-3 | Selector de idioma en header del landing | apps/landing | Design | TASK-i18n-2
feature-i18n-localization | TASK-i18n-4 | Migración columna locale en orders, quotes, complaints | services/api-core/prisma/migrations | DB | TASK-directpurchase-1, TASK-quoteB-1, TASK-complaint-1
feature-i18n-localization | TASK-i18n-5 | Middleware/decorator que lee X-Locale y persiste en el registro | services/api-core/src/modules/* | Design | TASK-i18n-4 | Toca módulos de otras features — coordinar antes de tocar
feature-i18n-localization | TASK-i18n-6 | Templates de email es/en (compra, cotización, recibo, reclamo, expiración, postponement) | services/api-core/src/modules/notifications-email | Design | TASK-i18n-4
feature-i18n-localization | TASK-i18n-7 | Módulo notifications-email selecciona template por locale del registro | services/api-core/src/modules/notifications-email | Design | TASK-i18n-6
feature-i18n-localization | TASK-i18n-8 | Traducción completa de textos UI landing (es/en) | apps/landing | Design | TASK-i18n-1
feature-i18n-localization | TASK-i18n-test1 | Unit tests: detección y persistencia de locale | services/api-core/src/modules/**/__tests__ | Design | TASK-i18n-7
feature-i18n-localization | TASK-i18n-test2 | Integration tests: locale a través de los flujos | apps/landing/src/__tests__ | Design | TASK-i18n-test1

## Dependencias
Feature origen | Depende de | Motivo
feature-direct-purchase | feature-catalog-landing | Re-lee precio/stock del catálogo
feature-order-delivery-schedule | feature-direct-purchase | UNION con tabla orders
feature-order-delivery-schedule | feature-custom-quote | UNION con tabla quotes
feature-payment-billing-java | feature-direct-purchase | Contrato HTTP de pagos
feature-payment-billing-java | feature-custom-quote | Link de pago para cotización
feature-realtime-notifications | feature-admin-auth-core | WS Gateway necesita JWT guard
feature-quote-management-admin | feature-custom-quote | Lee datos de quotes
feature-complaints-refunds | feature-payment-billing-java | Aprobación de reembolsos
feature-i18n-localization | feature-direct-purchase | Columna locale en orders
feature-i18n-localization | feature-custom-quote | Columna locale en quotes
feature-i18n-localization | feature-complaints-refunds | Columna locale en complaints
feature-supply-stock-management | feature-realtime-notifications | Alertas low-stock usan notifyAdmins()
feature-admin-auth-core | feature-realtime-notifications | Lockout envía notificación WS
feature-infra-deploy | feature-admin-auth-core | CI depende de TASK-auth-12
feature-infra-deploy | feature-payment-billing-java | Dockerfile payment-service